## Sheet1
A: Coherence
Priority | Recommendation | Timeframe | Action/ How | Lead co-ordinator and stakeholders | Indicator | Risks | Mitigating measure | Corresponds to which recommendation/action?
A 1. | Empower the National Commission as a consultation and decision-making body to ensure policy coherence and drive a more inclusive whole-of-society approach to development co-operation. | 2024 IV Q and on-going | A 1.1. Add items for decision to the agenda of the National Commission (i.e. start with the adoption of this action plan) | Lead MFA, all members of Commission able to add items on the agenda |  | Lack of buy-in from members despite these new incentives. | Link work with results agenda.
|  | 2025 I Q | A 1.2. Establish timebound working groups to handle specific operational or thematic issues: | Lead – MFA, involve all interested members | Realistic ToRs with clear tasks and objectives, its composition and decision-making process; roadmap for inclusive consultation and decision-making.
|  |  | 1.2.1. Establish a working group under the National Commission to drive a transparent and inclusive process for establishing the next Strategic Guidance on developing co-operation. (realistic ToRs with clear tasks and objectives; survey on how Lithuania is perceived by its implementing partners and partner country counterparts, working through embassies) | Lead - MFA
|  | 2025 II Q - continous | A 1.3. Maintain and coordinate the whole-of-government strategy on supporting recovery and reconstruction of Ukraine, e.g. by conducting bi-annual reviews of the implementation of the Guidelines for Lithuania's engagement in the recovery and reconstruction of Ukraine 2024-2027 (adopted by the Government of the Republic of Lithuania on 9 October 2024) | Lead – MFA, LRVK and CPVA | Reflected in agenda document on xx | Capacity constraints/ lack of buy in from members to attend or participate fully in meetings | Seek opportunities for the National Commission to feed into discussion in Parliament on Ukraine.
A 2. | Initiate discussions with targeted Parliamentarians to champion development co-operation issues and awareness in the Parliament and participate in working groups and meetings of the National Commission. | 2024 IV – 2025 II Q | A 2.1. Identify potential "champions" for development cooperation; consider the opportunities to promote the establishment of a "Friends" group for development cooperation; elaborate on the opportunities to hold a meeting of the National Commission for Development Cooperation at the Parliament, engaging parlamentarians | Lead - MFA, additional LRVK, members of National Commission |  | Upcoming election reshuffles the composition of the Parliament | Start engaging with individual parliamentarians after the new Parliament is in place.
Seek opportunities for the National Commission to feed into discussion in Parliament on Ukraine.
[6 empty] | Capacity constraints/ lack of buy in from members to attend or participate fully in meetings | Link work with results agenda.
[6 empty] | Plenty of legislative amendments, political will and additional resources will be required. | Link work with results agenda.
A 3. | Update and clarify mandates of key actors in Lithuania’s Development Co-operation ecosystem | On-going – regulations and description of activities (as approved by MFA) are currently under revision | A 3.1. Clarify the division of labour between the Office of the Government, MFA, MoF, CPVA, ILTE, EIMIN, Inovation Agency in view of existing mandates as per the National Law on Development Co-operation and Humanitarian Aid. Reflect on the potential need to change the Law accordingly. | MFA/MoF/CPVA/Office of the Government, others listed |  | Lack of agreement on the roles between institutions
|  |  | A 3.2. Reflect on whether there is a need to change legal acts to reduce fragmentation and establish clear leadership in development co-operation | MFA with the OECD |  | Lack of political will
|  |  | A 3.3. Elaborate on the options to strenghten a formal link between the MFA and CPVA | MFA, CPVA, MoF, LRVK
|  |  | A 3.4. Consider changing funding of CPVA to enable their broader participation in development cooperation | MFA and CPVA |  | Lack of will of provide more financial allocations for CPVA
A 4. | Craft Lithuanian development vision, including a rationale for Lithuania’s engagement, and embed it the strategic documents | 2025 I- IV Q | A 4.1. Identify the main vector (direction/goal) of Lithuanian development co-operation as a part of foreign policy. | Lead – MFA, include other members of National Commission
|  |  | A 4.2. Develop new strategic guidelines of Lithuanian development cooperation 2026-2030 with the goal to reach 0,33% of GNI as ODA allocations by 2030. Strategic guidelines including strategic and practical principles for a) private sector engagement ; b) CSOs engagement | Lead – MFA, include other members of National Commission
|  | 2025 I- IV Q | A 4.3. Use the Annual Development Conference as a strategic tool to: 1) promote strategic objectives of development cooperation, 2) communicate success stories and results, 3) invite external partners and experts to share insights and explore new partnerships. | MFA lead, together with the LRVK, CPVA. Consider ‘outsourcing’ lead for the design of the private sector and CSO partnership session to respective, relevant private sector and CSO actor, under supervision of MFA and CPVA | Next annual event includes at least one dedicated session to partnerships, involving relevant partners and high-level MFA representation. | Not enough time to fully revisit the schedule and approach to this annual event to be ready in fall this year. | Consider a later date for the event to have more time; or consider maintaining the similar approach as last years for ease of organisation and logistics and add one side-event specific on partnerships for this year, to be expanded upon in future events.
[6 empty] | Private sector and CSO actors have no capacity or are unwilling to lead on shaping up their respective sessions | Scope of the private sector and CSO sessions for this first ‘test’ year could be to socialise, discuss and act on the findings from the diagnostics and action plan actions.
[6 empty] | Duplication of discussion and events already undertaken by CPVA (high-level meetings in LT with those who are engaged in development cooperation) | CPVA and MFA to map and coordinate around relevant existing initiatives done by CPVA and keep each other informed systematically of ongoing events (if not yet done so, could imply setting a joint calendar of regular development cooperation meetings/events, ensure to invite relevant counterparts to events, etc)
A 5. | Build development capacities across your development co-operation system, starting by identifying and mobilising better the existing skills, expertise and capacity within the system. | 2025 I-III Q | A 5.1. Identify key capacity gaps and needs for short-, medium- and long-term, both across government actors and its key partners | Lead - MFA, CPVA, consulting other more active stakeholders. External partners, including CSOs, Academia and Think Tanks on International relations and security. | Staff in CPVA and MFA tasked with undertaking this action item. | No time nor resources to populate such a central repository of LT related development co-operation knowledge. | Consider building on CPVA’s existing approaches to collecting best practices on the ground, collecting expertise on public sector, at civil society level, etc. and its participation to Practitioners' Network with the EU Pillar Assessed agencies etc.
|  | 2025 I-III Q | A 5.2. Based on the above exercise, consider various options including training, HR reforms (longer term), use of consultants (tailored to different needs: quick fixes versus longer term hires under more flexible conditions, explore the potential of hiring local staff in Embassies – begin with Ukraine) |  | E.g. Questionnaire (internal to administration) developed to assess capacity needs in view of available expertise. Focus group discussion organised with key partners across Lithuania’s development co-operation ecosystem to identify expertise, willingness to engage with the administration and options to systematize these collaborations. |  | Consider how to expand the existing LTAid webpage, which is clear, simple and user-friendly with a specific section that organises development cooperation knowledge (tools, guidelines, success stories, etc.) and that can be used ‘for reference’ by staff
|  | Ongoing-2025 IV Q | A 5.3. Organize capacity building activities (i.e. thematic, invite OECD experts, use annual development co-operation meeting, etc. |  | XX capacity building activities organised
|  | 2025 II-III Q | A 5.4. Work with civil society partners (i.e. expert think tanks, academics, etc.) to establish ‘induction courses’ and/or training courses on key development co-operation concepts for the relevant staff) . |  | XX guidance/ tools identified and made available to staff
B: Private Sector
Priority | Recommendation | Timeframe | Action/ How | Lead co-ordinator and stakeholders | Indicator | Risks | Mitigating measure | Corresponds to which recommendation/action?
B 1. | Strenghthen consultation and information sharing mechanisms to attract and increase private sector engagement | Ongoing-2025 IV Q | B 1.1.Conduct systematic consultations (e.g. through the formation of a private sector sub-group within the National Commission or Economic Diplomacy Council) to create habits of collaboration | Lead - MFA, CPVA and Ministry of Economy and Innovations, Innovation Agency, Lithuanian Innovation Centre | National Commission Meeting attendance (short term) | Lack of buy in from business community + lack of agreement of which ministry/agency should lead this at operational level | Compile lessons learned from other donors on growing PPPs from a low base, increase outreach efforts, reporting to National Commission and consideration of an Annual Conference focus on building PPPs
|  | 2025 I-II Q | B 1.2. Conduct consultation on establishing or providing with mandate an institution/entity that would support engagement of private sector in development cooperation | Lead - MFA, consulting with LRVK, MoF, Ministry of Economy, CPVA, Innovation Agency | Agreement on the division of labour | Agreement may require for expansion of CPVA mandate and change of funding model |  | A 3.1
|  | Ongoing | B 1.3 Gather and publicize information on local and international tenders (starting with the tenders on Ukraine) of MDBs and international organisations (or provide access to existing databases, i.e. developmentaid.org, to LT companies) | Innovation Agency, Lithuanian Innovation Centre | Joint communication formats between institutions (e.g. information portal/map showing the opportunities within and beyond Lithuania.) Information (or link) provided in simple and accessible format, preferably jointly with other information on development cooperation (i.e. LTAid page).
|  | 2025 I Q - every six months | B 1.4 Conduct regular seminars/workshops (business breakfast or similar formats) for business community on developing markets (starting with Ukraine), development cooperation, invite CSOs to encourage networking and matchmaking | Innovation Agency together with MFA, CPVA, Ministry of Economy and Innovation
|  | 2025 II Q - continous | B 1.5 Organize partnership-building missions to developing markets (starting with Ukraine), including business, CSOs, public institutions | Innovation Agency together with MFA, CPVA, Ministry of Economy and Innovation, Lithuanian Innovation Centre
|  | Ongoing - 2025 IVQ | B 1.6 Analyze synergies and better utilize economic diplomacy network (starting with support to Ukraine) | MFA, CPVA, Ministry of Economy and Innovation, Innovation Agency | Include the topic of development cooperation and its possibilities in the agendas of economic diplomats and commercial attachés to: a) ensure faster and thorough dissemmination of information on opportunities for private sector b) ensure more engagement opportunities with other donors
B 2. | Develop incentives and financial instruments to enable private sector engagement | Ongoing – 2025 IV Q | B 2.1. Leverage the resources of the Fund to attract private and other sources of funding by: | Lead – MFA, CPVA, MoF |  | No ideas forthcoming from business | Information sessions to build capacity in the business community.
B 2.1.1. Establishing specific project proposals offering possibilities to join forces with private sector and other potential donors (start with Ukraine)
B 2.1.2. Create more open-ended calls of proposals, considering financing for: development of sustainable innovative idea, piloting of examples on the ground, seed funding, finding partnerships, coverage of concessional financing conditions, diminishing risks.
B 2.1.3 Develop an application process for co-funding
|  | 2026 - 2027 | B 2.2. Consider establishing a longer-term grant-based mechanism, for example by adapting good practices examples (FinnPartnerships or Ukraine Partnership Facility (Netherlands))to Lithuanian context | MFA, CPVA, Innovation Agency
|  | 2025 II Q | B 2.3. Elaborate on the mechanisms for collaboration between public sector, CSOs and businesses/business associations: encouraging applications that involve partnerships between CSOs (e.g. Lithuanian and in partner countries) and public/private sector entities, philanthropy, research sectors by communicating that project proposals with meaningful partnerships will be provided more points in the selection process. | MFA/CPVA/NGDO platform | Stating in the application form and related guidance that projects involving partnerships will be prioritised. |  |  | C 2.7.
|  | Ongoing – 2025 II Q | B 2.4. Providing clear communication to applicants on application requirements and selection criteria (i.e. reader-friendly guide, FAQs, videos) | CPVA | Communication material produced and or updated. | Communication material is not used by project applicants. | Consultations with project applicants can help ensure that the material produced/updated is responsive to applicants' needs. | C 2.8.
|  | 2025 I-IV Q | B 2.5. Streamline collaboration between CPVA and MFA for evaluating projects applications e.g. by adopting a two-stage application process (stage 1 - project description + basic administrative requirements. Stage 2 - more robust administrative requirements) Complementary knowledge: MFA could rate proposals on how those meet development co-operation priorities and objectives, CPVA could focus on administrative, financial and capacity-related requirements. | MFA/CPVA | Two-stage selection process piloted in the call for proposals. | Increasing workload for CPVA and MFA | MFA and CPVA collaboratively develop efficient processes to avoid duplication of work and smooth communication. | C 2.9.
B 3. | Expand development finance instrument capabilities | 2026-2027 | B 3.1. Participation in the OECD DAC Community of Practice on Private Finance (PFSD) and related formats to build knowledge on development co-operation instruments and engage regularly with DFIs and other stakeholders | ILTE or other relevant institution | One new instrument designed by end of project phase in 2025. | Lack of demand from business sector; lack of funding for establishment of a financial instrument | A) Lessons from other development co-operation providers on growing demand for PPPs from a low base (Finland, Denmark). Plus, further investigation of potential for take-up during private sector pilot phase. B) Explore all opportunities to reallocate existing funding; put efforts to secure new funding in the upcoming budgetary cycle.
|  |  | B 3.2. Elaborate on the options to establish a suite of financing instruments for development co-operation: | MFA and MoF
|  |  | B 3.2.1. In collaboration with partners, consider new financing instrument/s while also supporting the identification of needs and opportunities in partner countries: a) Consider joining existing financial instruments in Nordic countries to learn how to create, manage, develop such instruments b) Propose a guarantee or loan based (or mixed) financial instrument to enhance the ability of private sector to engage in larger projects | MFA, MoF, ILTE
C: Civil Society
Priority | Recommendation | Timeframe | Action/ How | Lead co-ordinator and stakeholders | Indicator | Risks | Mitigating measure | Corresponds to which recommendation/action?
C 1. | Strenghthen already existing and establish new consultation and capacity-building mechanisms to increase civil society engagement and build long-term trust-based relations | Ongoing | C 1.1. Conduct regular consultations to inform the design of the calls for proposals (with domestic and partner-country CSOs), establishment of new instruments, monitoring and evaluation, changes in development cooperation policy, etc. | MFA | Conducting at least one consultation session (hybrid meeting or in writing) with Lithuanian and partner-country CSOs and other potential project applicants in every round of call for proposals (hence annually). | Lack of sufficient participation to the consultation process by CSOs | Well communicating the rationale of consultations to CSOs
[6 empty] | Lack of belief that consultations will have an impact on the priority-setting process | Organising channels for both oral and written contributions to ensure maximum participation
Closing the consultation loop by reporting back how inputs by CSOs guided the priority-setting for the call for proposals
|  | 2025 I Q | C 1.2. Consider ways to encourage Lithuanian CSOs participation in DAC CSO networks/workshops | MFA with Ministry of Social Security and Labor, Active Citizens Fund, NGO Fund
|  | 2024 IV Q | C 1.3. Appoint one dedicated staff person to exchanges with CSOs to help ensure continuity of relations and sharing of knowledge with the next focal point | MFA | Appointed staff person | High turnover rate of staff appointed as CS focal point | Appointing a shadow person with a different rotation time than the focal point, who would remain on the copy of all exchanges with CSOs.
C 2. | Develop incentives and financial instruments to attract civil society engagement | 2025 III-IV Q | C 2.1. Consider allowing submission of project proposals that cover periods longer than two years, by aligning the maximum project budget allocation to fund these projects | MFA, CPVA | Increase in the number of projects with a funding period of more than 2 years | Decrease in the number of projects funded, due to budgetary limitations | Reconsidering the total budget of the Fund
|  | 2024 IV-2025 II Q | C 2.2. Exchanging with the Governing Board of the Fund to review/remove the 10% co-funding requirement for CSOs | MFA, Governing Board of the Fund | Updating the selection criteria accordingly to reflect the removal of the 10% co-funding requirement | Exchanging with the Governing Board of the Fund to review/remove the 10% co-funding requirement for CSOs or accept in-kind contributions
|  | 2026-2027 | C 2.3. Developing a new funding instrument (i.e. framework agreements) and identifying legal requirements for financing selected partners (potentially medium to large CSOs) that meet the pre-defined criteria (e.g. experience in running multi-year programmes, personnel and financial capacities, network). Ensure coherence with Civil society recommendations for new mechanisms. | MFA, CPVA, Governing Board of the Fund | The funding instrument is piloted in the next funding cycle | Increasing workload for both institutional actors and for CSOs to meet due diligence requirements.
Lack of funding.
|  | 2025 I Q - continous | C 2.4. Establishing specific project proposals offering possibilities to join forces with private sector and other potential donors (start with Ukraine) | MFA, CPVA, Governing Board of the Fund
|  | 2025 I - II Q | C 2.5. Create more open-ended calls of proposals, increasing space for applicants' own right of initiative by adding thematic flexibility while still meeting the overarching objectives/priorities of Lithuanian development cooperation | MFA, CPVA, Governing Board of the Fund
|  | 2025 IV Q | C 2.6. Adjust existing instruments (e.g. co-funding modality) to provide reimbursable funds (to support access to other international donors and EU funds) | MFA, CPVA
|  | 2025 III-IV Q | C 2.7. Continue exploring the possibility of attracting well-established Lithuanian CSOs into the field of development cooperation | MFA, CPVA
|  | 2025 II Q | C 2.8. Set-up mechanisms for collaboration between CSOs and businesses/business associations: encouraging applications that involve partnerships between CSOs (e.g. Lithuanian and in partner countries) and public/private sector entities, philanthropy, research sectors by communicating that project proposals with meaningful partnerships will be provided more points in the selection process. | MFA/CPVA/NGDO platform | Stating in the application form and related guidance that projects involving partnerships will be prioritised. |  |  | B 2.4.
|  | Ongoing – 2025 II Q | C 2.9. Providing clear communication to applicants on application requirements and selection criteria (i.e. reader-friendly guide, FAQs, videos) | CPVA | Communication material produced and or updated. | Communication material is not used by project applicants. | Consultations with project applicants can help ensure that the material produced/updated is responsive to applicants' needs. | B 2.5.
|  | 2025 I-IV Q | C 2.10. Increasing collaboration between CPVA and MFA for evaluating and shortlisting projects applications e.g. by adopting a two-stage application process (stage 1 - project description + basic administrative requirements. Stage 2 - more robust administrative requirements) Complementary knowledge: MFA could rate proposals on how those meet development co-operation priorities and objectives, CPVA could focus on administrative, financial and capacity-related requirements. | MFA/CPVA | Two-stage selection process piloted in the call for proposals. | Increasing workload for CPVA and MFA | MFA and CPVA collaboratively develop efficient processes to avoid duplication of work and smooth communication. | B 2.6.
D: Other donors/partnerships
Priority | Recommendation | Timeframe | Action/ How | Lead coordinator and stakeholders | Indicator | Risks | Mitigating measure | Corresponds to which recommendation/action?
D 1. | Indentify and leverage opportunities for partnerships with other donors | Ongoing | D 1.1. Building on successful institutional cooperation (Twinning/TAIEX) to find opportunities to scale and/or involve private sector/ CSOs | MFA, CPVA, embassies working with key state and non-state partners, Innovation Agency | Establish a regularly updates list with potential opportunities | Limited capacity and instruments to support partnerships | Sequenced approach in building capacities for partnership, including through buying in expertise and increasing number of incentives for partnerships based on other reforms in this project
|  | Ongoing | D 1.2. Work with other donors in priority countries (starting with Ukraine) to explore new opportunities for partnering in projects and instruments. | MFA and CPVA with ILTE and other state/non-state partners, Innovation Agency | Discussions launched on new partnership activities | Limited private sector demand for working in developing countries. Limited instruments to incentivise partnerships | Increasing knowledge across Lithuania’s development ecosystem and support from other donors in the region with longer experience in PPPs.
|  | Ongoing | D 1.3. Build on existing partnerships and scale up cooperation | Lead – CPVA and MFA, make use of partnerships established for the reconstruction of Ukraine
D 2. | Scale up partnerships with the European Union institutions | Ongoing | D 2.1. Scale up advocacy efforts (working closely with other small donors) to increase partnership opportunities through Team Europe, the Global Gateway and other initiatives (e. g through consolidated information platforms, formal incentives for partnerships between smaller and larger donors, reduced credit and insurance costs for non-state actors) | MFA and LT Permanent Representation in EU | Discussions launched on new partnership opportunities. | Bilateral programmes more accountable to Brussels than to members. | The increasing focus on EU geostrategic interests, including links to the role of private sector in helping to pursue these interests in developing countries.
[5 empty] | Included in priorities for LT presidency of the Council of the EU in 2027 | Significant financial and management capacity required to manage these partnerships.
Increased participation in procurement processes
Increased number of partnerships
|  | Ongoing | D 2.2. Work with other donors in priority countries to form Team Europe initiatives | MFA, ILTE and CPVA with state and non-state partners | Discussions launched on new partnership activities | Limited private sector demand for working in developing countries. Limited instruments to incentivise partnerships | Increasing knowledge across Lithuania’s development ecosystem and support from other donors in the region with longer experience in PPPs.
|  | Ongoing | D 2.3. Seek continuity of implemented action by scaling up established cooperation to develop partnerships | Lead – CPVA, make use of multiple cases of cooperation through Twinning and other programmes where Lithuania (CPVA) led the process and managed projects with other agencies and institutions
E: Results, Monitoring and Evaluation
Priority | Recommendation | Timeframe | Action/ How | Lead co-ordinator and stakeholders | Indicator | Risks | Mitigating measure | Corresponds to which recommendation/action?
E 1. | Use pilot partnerships to refine M&E approaches with different types of partners | Ongoing – 2025 IV Q | E 1.1. Help desk function during implementation of the pilots to provide advice and refine guidance. Identify targets and evaluation criteria for each of the pilots. | MFA, CPVA with OECD team support
|  | 2025 II Q | E 1.2. Workshop to stocktake and share tailored Results and M&E toolkit | MFA, CPVA with OECD team support
E 2. | Plan how to evaluate the ODA portfolio - develop an evaluation policy document in line with DAC criteria and principles tailored to Lithuanian context | Ongoing – 2025 IV Q | E 2.1. Start with pilots and/or Ukraine programme in a broader sense | MFA, CPVA, LRVK, other involved stakeholders | Evaluation policy document aligned to DAC principles and criteria | Lack of practice of project evaluations by Lithuania and Ukraine external partner (high level evaluations are done so far) | Conduct few evaluations focused on large projects and get expert support
E 3. | Institutionalising the Monitoring, Evaluation, and Learning (MEL) system | 2025 II – III Q | E 3.1. Mainstreaming the approach: Define clear targets and indicators to enable progress measurement and results reporting (decide where they should be reflected, i.e. strategic guidelines, project descriptions, etc.) | MFA, CPVA with OECD team support | Introduce basic logical framework or results framework in the project document for financially substantial interventions on a pilot basis | Lack of human and financial resources to hold the dialogue with implementers - be mindful of the staff time needed for M&E when designing the M&E system | Ensure the M&E systems is not burdensome - focus on outcomes
|  | 2025 II – III Q | E 3.2. Mainstreaming the approach: Look at ways to co-create and have a dialogue with partners (CSOs and private sector) during implementation to share a common vision beyond mere reporting exercises
|  | 2025 IV – 2026 I Q | E 3.3. Increasing capabilities: design a plan to strengthen internal skills building on MEL system and the toolkit (e.g. training plan with certification, focal point) | MFA, CPVA | Develop training materials | Training materials are insufficient to help staff and implementers use the MEL system properly | Make sure guidance and focal points are available to answer most common questions. Align the guidance to EU’s or OECD’s standard guidance.
|  | 2025 III – IV Q | E 3.4. Feedback loop: define headlines indicators that can be aggregated and used for steering and adapting programming- Facilitate knowledge sharing among programme managers | MFA, CPVA with OECD team support | A limited series of headline indicators associated to Lithuania’s main development co-operation priorities is established. Existing mechanisms (annual meeting) include a segment to review and discuss results, with an emphasis on lessons-sharing. | Data that can be aggregated is limited or incomplete | Focus on few (5-6) output indicators in areas or sectors where Lithuania finances several projects, encouraging the monitoring of such indicators (when relevant) during implementation. Complement quantitative indicators with qualitative analysis of change due to Lithuanian projects, lessons capturing and sharing.
|  | 2025 IV – 2026 I Q | E 3.4. Iterative refinement: learn from other countries (e.g. Finland) how to develop the Results-based management (RBM) system over time. | MFA, CPVA | Revise the action plan based on lessons and good practices identified through exchanges with peer DAC country
E 4. | Start to communicate results, including to Parliament (and considering reporting progress on the DG reform project) | 2024 IV Q | E 4.1. Start by systematically harnessing results data and info from existing reporting processes (to the EU on Twinning, policy coherence, etc.) | MFA, CPVA with collaboration with other Lithuanian stakeholders to get the right information | Results are communicated at the annual event on development co-operation | Lack of time to collect results and process not in place to aggregate quantitative data | Start with communicating qualitative information (3 to 4 illustrative stories) on results achieved
|  | 2024 IV – 2025 II Q | E 4.2. « Crowd-source » the collection of headline results and success stories to external partners (i.e. through annual reporting requesting inputs on specific results, or to publicize and cross-reference on partner’s website (where relevant and according to partner’s rules, etc.)
|  | 2024 IV – 2025 II Q (in line with progress on engaging Parliament) | E 4.3. Consider an annual communication schedule for development co-operation related information.
|  | 2025 IV Q (next Annual event planned in fall 2025) | E 4.4. Use Lithuania annual development cooperation event to invite higher level participants (beyond project implementers)
|  | 2025 IV Q (next Annual event planned in fall 2025) | E 4.5. Consider organising a dedicated side event at Lithuania’s annual development co­-operation event to communicate on results